## Sheet1
BugID | TestID | Description | Severity (1 - 5) | Reason | Assigned | Completed
1 | add.2 | When adding playlist to spotify, if the button is double clicked a duplicate request will be sent | 2 | Duplicate request does not cause any problems with the playlist, but is still an extra unnessesary api call |  | in progress
2 | share.2 | When sharing a playlist and 0 phone numbers input, recent people includes a 'null' value | 2 | Null value can be ignored, but may confuse users | liam | 2016-12-04
3 | data.1 | When a null value is passed into database of recent numbers, it is stored instead of discarded | 1 | Does not affect program performance, but is still an undesired result | liam | 2016-12-04
4 | ui.3 | Occasional 500 internal server error when attempting to login via spotify | 3 | Not common, but prevents users from using our service when it occurs |  | in progress